## Blank
Days for Calc
Release Day | 0 | 2022-07-12
Post Beta Reader Form | 147 | 2022-02-15
Contact Beta Readers | 140 | 2022-02-22
Announce Book, Synopsis, Webpage | 110 | 2022-03-24
Beta Comments Due | 95 | 2022-04-08
Create Book Page for Press Kit | 94 | 2022-04-09
Update List of Reviewers | 88 | 2022-04-15
Create cover (or hire someone) | 85 | 2022-04-18
Announce Release Date | 76 | 2022-04-27
Hire editor | 75 | 2022-04-28
Build list of blurb people | 74 | 2022-04-29
Send out blurb requests | 73 | 2022-04-30
Create hardback cover & interior | 69 | 2022-05-04
Post ARC Form/Make requests | 67 | 2022-05-06
Set up HB on IngramSpark | 64 | 2022-05-09
Finalize Cover (less blurbs) | 60 | 2022-05-13
Create Book on Goodreads | 59 | 2022-05-14
Reveal Book Cover on SM | 58 | 2022-05-15
Preorder Amazon w/ cover | 57 | 2022-05-16
Set up ads on Amazon, FB | 56 | 2022-05-17
BookBub New Release Sub | 55 | 2022-05-18
Order HB for Proof | 54 | 2022-05-19
Set up Blog Tour | 53 | 2022-05-20
Netgalley Request | 46 | 2022-05-27
Finalize Author Press Kit | 37 | 2022-06-05
Set up Goodreads Giveaway | 36 | 2022-06-06
Contact Bookstores | 31 | 2022-06-11
POST: 1st book excerpt | 24 | 2022-06-18
POST: 2nd book excerpt | 12 | 2022-06-30
Setup SM posts for 4-8 weeks post release | 10 | 2022-07-02
POST: 3rd book excerpt | 3 | 2022-07-09
Post Paperback to Amazon | 2 | 2022-07-10
Set up FB ads to run for 1 week | 1 | 2022-07-11
Release Day | 0 | 2022-07-12
Remind Early Readers to leave review | -1 | 2022-07-13
Return Price | -7 | 2022-07-19